## Sheet1
ID | Theme | As an | User story | to | Notes | Priority | Status
1 | Database | Developer | I want to create a database to store and get data about users | see data on the site and use it in the API | Need synchronization with API | High | Work in progress
2 | API | Developer | I want to create an API to be able to work with the database | Do queries on the database and return that to app/website | Synchronization with database/webserver and app | High | Work in progress
3 | Server | Developer | i want to automatically upload git pushes with regards to the website to the server | Avoid the extra work to that manually |  | Medium | Done
4 | Website | Developer | Basic lay-out where all functionality can be displayed | be able to test the functionality |  | Medium | Work in progress
5 | Website | User | I want to be able to create an account and login | be able to use the site and be contacted |  | Medium
6 | Website | User | I want to link my account with social media | display my personal information and qualifications | Requires working with multiple Social Media API And some form of verification.
7 | Website | User | I want to offer tutoring for multiple subjects | find customers to give tutoring to
8 | Website | User | I want to look for tutoring on a subject and academic level and find the list of tutors with their ratings and their location | find a tutor efficiently and see their rating in a clear way and at the same time disregard tutors out of My living and working area
8 | Website | Developer | I want to develop a way to match location of a user and a tutor | effectively display possible tutors based on Customers' information
9 | Website | User | I want to see the personal information of tutors and have their Facebook (or other social media) linked | see what the tutor is like, if he is qualified and if he Is trustworthy
9 | Website | User | I want to make contact with the tutor to make an arrangement | set up a tutoring session
10 | Website | User | I want to be able to rate my tutor and leave behind a general Impression of him or her | rate him or her and inform possible future customers And the site about his/her performance | Requires some validation of the rating. Need Confirmation that the meeting has actually happened
11 | Website | Moderator | I want to make sure the integrity of the site and tutors is Not comprimised by having spam or unserious tutors | Maintain the integrity of the site | Requires some threshold which makes the Apperance of unserious tutors less likely